## Slide 1
SMU GUILDHALL · PRODUCTION PLAN
DETECTIVE
FOLDER
From Studio Demo to Live-Service Mobile Game
Present by Young Gou
Notes: Title. Detective Folder was a studio demo — a 2D paper-folding puzzle-platformer. This deck: how we turn it into a live-service mobile game.

## Slide 2
THE CASE FILE WE START FROM
The demo we already built
CORE LOOP
Walk → Jump → Fold
SECONDARY LOOP
Explore → Collect → Avoid
THE GOAL
Catch the Baahd Guys
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
01
THE DEMO
Notes: 2D paper-folding puzzle-platformer. The fold mechanic is the identity. Shipped: tutorial + 4 levels. This is the loop we must not break.

## Slide 3
THE STRATEGIC BET
Keep the loop. Build a live game around it.
PROTECT
The fold loop, the 4 levels, the noir story.
REBUILD
The same systems, remade for touch & content.
ADD
Progression, LiveOps, monetization, backend, QA.
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
02
THESIS
Notes: The through-line: protect / rebuild / add. Low risk to the fun, high investment on the surrounding machine.

## Slide 4
PROJECT BREAKDOWN · 11 FEATURES
The conversion at a glance
CARRIED OVER · DF 1–6
DF 1
Core gameplay
DF 2
Level system
DF 3
Character system
DF 4
Environment & objects
DF 5
Comic narrative
DF 6
UI & menu system
NEW LIVE-SERVICE SYSTEMS · DF 7–11
DF 7
Player progression
DF 8
LiveOps & events
DF 9
Monetization
DF 10
Online & backend
DF 11
QA & compatibility
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
03
BREAKDOWN
Notes: Six features carry the demo forward; five are net-new. Deferrals are deliberate scope discipline.

## Slide 5
LOCKED PRODUCT DEFINITION
What we are actually shipping
~45
days per version
~8
versions / year
3
monetization pillars
0
gacha · 0 ads
Narrative-driven detective live-service game. Monetization: battle pass + monthly card + skin shop.
EXPLICITLY OUT OF SCOPE
UGC / editor deferred
Localization deferred
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
04
SCOPE
Notes: Locked definition. Deferrals stated up front. No gacha is a positioning choice.

## Slide 6
FEATURES 1–6 · TO MOBILE
Reworking the core for mobile
1
Touch controls
2
Level toolset
3
Cosmetic skins
4
Extensible objects
5
Store screens
6
English pipeline
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
05
CORE REWORK
Notes: The fold loop is untouched; the container around it becomes mobile-native and content-scalable.

## Slide 7
FEATURES 7–11 · THE MACHINE
Five new systems make it live
DF 7
Player progression
Retention spine
DF 8
LiveOps & events
Events · economy · A/B
DF 9
Monetization
Battle pass · card · skins
DF 10
Online & backend
Accounts · save · analytics
DF 11
QA & compatibility
Devices · cert · regression
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
06
NEW SYSTEMS
Notes: Features 7-11 — where headcount and cost go. No ads, no gacha. Shared case archive replaces a leaderboard.

## Slide 8
MILESTONE SCHEDULE · MS0 → MS6
The roadmap
MS0
Oct 2026
Pre-Production
MS1
Apr 2027
Alpha
MS2
Jul 2027
Content Complete
MS3
Oct 2027
Beta
MS4
Dec 2027
Launch
MS5
Jan 2028
Archive
MS6
2028+
Live Template
◀ BUILD PHASE
LIVE SERVICE ▶
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
08
ROADMAP
Notes: ~14 months of build (MS0 to launch MS4 Dec-2027), then MS5 archive and MS6 as the repeating template.

## Slide 9
TWO PHASES
From building the game to running it
BUILD · MS0–MS4
Make the game and ship it
1
Prototype proves the fold loop on mobile
2
Levels 1–4 content-complete; store UI
3
Cert, IAP, Gold Master — launch
LIVE · MS5–MS6
Archive, then run the engine
Archive source, tools & pipelines (MS5)
Ship a new version every 45 days (MS6)
Data tunes the next cycle — full speed through 2028
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
09
BUILD → LIVE
Notes: Left = the build campaign. Right = life after launch. MS6 is a repeatable template; 2028 is full-speed content.

## Slide 10
THE HEART OF A LIVE GAME
The 45-day content engine
Days 1–15
Greybox
›
Days 15–30
Alpha
›
Days 30–45
Shippable
EVERY CYCLE SHIPS
2 levels + case
1 character
1 pass + skin
1 extra skin
1 event
~8 level-equivalents are built before launch, so the cadence starts full-speed on day one.
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
07
CONTENT ENGINE
Notes: The operational core. Staggered 45-day pipeline + pre-launch runway make live-service real.

## Slide 11
STAFFING PLAN · HEADCOUNT
Ramp to a runway, then sustain
Chart: 
| Signing | Pre-Prod | Production | Alpha | Beta | RC | Live Ops
Headcount | 3 | 9 | 23.5 | 28 | 38.5 | 38 | 35.5
38.5
peak (Beta)
~20–24
steady live-ops
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
10
STAFFING
Notes: Ramp, peak at Beta to bank a content runway, then build/systems roles exit while narrative, content, LiveOps and QA persist.

## Slide 12
COST & RESOURCING
What the plan costs
$9.63M
TOTAL LABOR COST
951.5
TOTAL MAN-MONTHS
43
ROLES · 8 TEAMS
38 in-house across 8 feature teams + 5 outsourced vendors. Salaries benchmarked to the 2025 GDC Salary Report.
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
11
BUDGET
Notes: $9.63M labor, 951.5 man-months, 43 roles. Vendors are batched commissions. Salary method is documented and defensible.

## Slide 13
KEY DECISIONS & RISKS
What we chose, and what we watch
Protect the core loop
Deliberate
Cosmetic-only revenue
Positioning
Content pace
Risk → mitigated
Deferred scope
Watch
DETECTIVE FOLDER · DEMO → LIVE-SERVICE
12
DECISIONS
Notes: The judgment calls: keep the loop, no gacha, sustain content pace by batching audio/VO, park UGC/localization/publishing.

## Slide 14
THE PATH FORWARD
From a folded page
to a living game
Keep the fold loop; rebuild for mobile.
Launch Dec 2027 on a pre-built runway.
Run a 45-day engine — ~8 versions a year.
Detective Folder · SMU Guildhall
Notes: Close on the through-line: loop protected, machine built around it, costed and scheduled end to end.

## Slide 15
Any Questions?
Thanks for Listening!
Detective Folder · SMU Guildhall
Notes: Close on the through-line: loop protected, machine built around it, costed and scheduled end to end.