## Staffing
DetectiveFolder - Live-Service Mobile Game
Staffing Plan
[5 empty] | Signing | First Playable | [8 empty] | Alpha |  |  | Beta |  |  | RC (Cert / RTM) |  | Release / Live Service | [20 empty] | Total Man Months Per Phase Per Dept
|  | (Catagories) |  |  | Signing | Pre-Production | Pre-Production | Pre-Production | Production | Production | Production | Production | Production | Production | Alpha | Alpha | Alpha | Beta | Beta | Beta | RC | RC | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM
|  | [PROJ. NAME] SCHEDULE | [41 empty] | Signing | Pre-Production | Production | Alpha | Beta | RC | PM | TOTAL
|  |  | Art |  | 0.5 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4.5 | 4.5 | 4.5 | 6.5 | 6.5 | 6.5 | 6 | 6 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 |  | 0.5 | 3 | 24 | 13.5 | 19.5 | 12 | 84 | 156.5 | Art
|  |  | Code |  | 0.5 | 2 | 2 | 2 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 9.5 | 9.5 | 9.5 | 10 | 10 | 7.5 | 7.5 | 7.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |  | 0.5 | 6 | 45 | 22.5 | 28.5 | 20 | 82 | 204.5 | Prog
|  |  | Production |  | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 1 | 3 | 9 | 6 | 9 | 8 | 63 | 99 | Production
|  |  | Design |  | 1 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 7.5 | 7.5 | 7.5 | 8.5 | 8.5 | 8.5 | 9.5 | 9.5 | 8 | 8 | 8 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 |  | 1 | 12 | 36 | 22.5 | 25.5 | 19 | 134.5 | 250.5 | Design
|  |  | Level Art |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 6 | 4.5 | 4.5 | 3 | 20 | 38 | Level Art
|  |  | UI |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 6 | 3 | 4.5 | 4 | 21.5 | 39 | UI
|  |  | Aud |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 |  | 0 | 0 | 0 | 0 | 9 | 0 | 21 | 30 | Aud
|  |  | QA |  | 0 | 1 | 1 | 1 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |  | 0 | 3 | 15 | 12 | 15 | 10 | 79 | 134 | QA
[5 empty] | 3 | 9 | 9 | 9 | 23.5 | 23.5 | 23.5 | 23.5 | 23.5 | 23.5 | 28 | 28 | 28 | 38.5 | 38.5 | 38.5 | 38 | 38 | 35.5 | 30.5 | 30.5 | 27.5 | 22.5 | 22.5 | 27.5 | 22.5 | 22.5 | 27.5 | 22.5 | 22.5 | 27 | 22 | 22 | 27 | 22 | 22 | 27 | 22 |  | 3 | 27 | 141 | 84 | 115.5 | 76 | 505 | 951.5
[5 empty] | 2026 | [5 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Department | Where? | Role | Employee | Cost/Mo. | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | Per Person Man Months Per Phase | [7 empty] | Cost per Dev
LEADERSHIP / CORE
Production | In-house | Executive Producer | Roland | 16000 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 1 | 3 | 6 | 3 | 3 | 2 | 11.5 | 29.5 | 472000
Design | In-house | Creative Director | Lilith | 15000 | 2026 Jul: 0.5; 2026 Aug: 1; 2026 Sep: 1; 2026 Oct: 1; 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0.5 | 3 | 6 | 3 | 3 | 2 | 1.5 | 19 | 285000
Code | In-house | Tech Lead | Mordecai | 15000 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 3 | 6 | 3 | 3 | 2 | 11.5 | 29 | 435000
Art | In-house | Art Director | Brick | 14000 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 3 | 6 | 3 | 3 | 2 | 10 | 27.5 | 385000
Design | In-house | Lead Designer | Axton | 13000 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 3 | 6 | 3 | 3 | 2 | 11.5 | 29 | 377000
NARRATIVE TEAM
Design | In-house | Narrative Lead | Maya | 11000 | [39 empty] | 0 | 3 | 6 | 3 | 3 | 2 | 20 | 37 | 407000 | bar: 2026 Aug to 2029 Aug
Design | In-house | Writer 1 | Salvador | 9000 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 3 | 3 | 3 | 2 | 20 | 31 | 279000
Design | In-house | Writer 2 | Zer0 | 9000 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 3 | 3 | 3 | 2 | 20 | 31 | 279000
CONTENT TEAM - CREATION STREAM
Design | In-house | Level Designer A1 | Krieg | 9000 | [39 empty] | 0 | 0 | 6 | 3 | 3 | 2 | 0 | 14 | 126000 | bar: 2026 Nov to 2027 Dec
Design | In-house | Level Designer B1 | Gaige | 9000 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 1.5 | 1.5 | 1 | 20 | 24 | 216000
Level Art | In-house | Environment Artist A1 | Athena | 8000 | [39 empty] | 0 | 0 | 6 | 3 | 3 | 2 | 0 | 14 | 112000 | bar: 2026 Nov to 2027 Dec
Level Art | In-house | Environment Artist B1 | Wilhelm | 8000 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 1.5 | 1.5 | 1 | 20 | 24 | 192000
Art | In-house | Character / Cosmetic Artist 1 | Nisha | 9000 | [39 empty] | 0 | 0 | 6 | 3 | 3 | 2 | 0 | 14 | 126000 | bar: 2026 Nov to 2027 Dec
Art | In-house | Character / Cosmetic Artist 2 | Claptrap | 9000 | [10 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 1.5 | 3 | 2 | 20 | 26.5 | 238500
CONTENT TEAM - INTEGRATION STREAM
Production | In-house | Content Producer | Jack | 10000 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0 | 0 | 3 | 3 | 3 | 2 | 11.5 | 22.5 | 225000
Code | In-house | Content Programmer 1 | Aurelia | 11000 | 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0 | 0 | 6 | 3 | 3 | 2 | 1.5 | 15.5 | 170500
Code | In-house | Content Programmer 2 | Amara | 11000 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0 | 0 | 0 | 0 | 3 | 2 | 11.5 | 16.5 | 181500
Art | In-house | Technical Artist | FL4K | 11000 | [39 empty] | 0 | 0 | 6 | 3 | 3 | 2 | 20 | 34 | 374000 | bar: 2026 Nov to 2029 Aug
GAMEPLAY TEAM
Code | In-house | Gameplay Programmer A | Moze | 12000 | 2026 Aug: 0.5; 2026 Sep: 0.5; 2026 Oct: 0.5; 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0 | 1.5 | 6 | 3 | 3 | 2 | 1.5 | 17 | 204000
Code | In-house | Gameplay Programmer B | Zane Flynt | 12000 | 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0 | 0 | 6 | 3 | 3 | 2 | 1.5 | 15.5 | 186000
Design | In-house | Systems Designer | Claptrap (CL4P-TP) | 9000 | 2026 Aug: 1; 2026 Sep: 1; 2026 Oct: 1; 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0 | 3 | 6 | 3 | 3 | 2 | 1.5 | 18.5 | 166500
Art | In-house | Animator | Dr. Zed | 8000 | [39 empty] | 0 | 0 | 6 | 3 | 3 | 2 | 20 | 34 | 272000 | bar: 2026 Nov to 2029 Aug
PLATFORM TEAM
Code | In-house | Backend / Online Programmer | Marcus Kincaid | 13000 |  | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 1.5 | 6 | 3 | 3 | 2 | 20 | 35.5 | 461500
Code | In-house | Tools Programmer | Mad Moxxi | 11000 | 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0 | 0 | 6 | 3 | 3 | 2 | 1.5 | 15.5 | 170500
Code | In-house | UI Programmer | Scooter | 10000 | 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0 | 0 | 6 | 3 | 3 | 2 | 1.5 | 15.5 | 155000
UI | In-house | UI Artist | Ellie | 8000 | 2026 Nov: 1; 2026 Dec: 1; 2027 Jan: 1; 2027 Feb: 1; 2027 Mar: 1; 2027 Apr: 1; 2027 May: 1; 2027 Jun: 1; 2027 Jul: 1; 2027 Aug: 1; 2027 Sep: 1; 2027 Oct: 1; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 0.5; 2028 Feb: 0.5; 2028 Mar: 0.5 |  | 0 | 0 | 6 | 3 | 3 | 2 | 1.5 | 15.5 | 124000
Code | In-house | Build / Release Engineer | Crazy Earl | 12000 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0 | 0 | 3 | 1.5 | 3 | 2 | 11.5 | 21 | 252000
LIVEOPS TEAM
Production | In-house | LiveOps Producer | Sir Hammerlock | 11000 | [13 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 1.5 | 2 | 20 | 23.5 | 258500
Design | In-house | Event Designer | Tiny Tina | 8000 | [13 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 1.5 | 2 | 20 | 23.5 | 188000
Design | In-house | Economy Designer | Patricia Tannis | 9000 | [13 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 1.5 | 2 | 20 | 23.5 | 211500
Code | In-house | Event Programmer | Mr. Torgue | 10000 | [13 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 1.5 | 2 | 20 | 23.5 | 235000
UI | In-house | LiveOps UI Artist | Ava | 8000 | [13 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 1.5 | 2 | 20 | 23.5 | 188000
Production | In-house | Data Analyst | Vance | 10000 | [13 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 1.5 | 2 | 20 | 23.5 | 235000
QA
QA | In-house | QA Lead | Handsome Jack | 9000 |  | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0 | 1.5 | 6 | 3 | 3 | 2 | 11.5 | 27 | 243000
QA | In-house | QA Automation / Test Tools | Tyreen Calypso | 10000 |  | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [9 empty] | 0 | 1.5 | 6 | 3 | 3 | 2 | 7.5 | 23 | 230000
QA | In-house | Content / Narrative QA | Troy Calypso | 6000 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 3 | 3 | 3 | 2 | 20 | 31 | 186000
QA | In-house | QA Tester |  | 6000 | [10 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 1.5 | 3 | 2 | 20 | 26.5 | 159000
QA | In-house | QA Tester |  | 6000 | [10 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 1.5 | 3 | 2 | 20 | 26.5 | 159000
EXTERNAL VENDORS
Aud | Outsource | Audio Design | Vendor | 9000 | [39 empty] | 0 | 0 | 0 | 0 | 3 | 0 | 7 | 10 | 90000 | bar: 2027 Aug to 2027 Oct; 2028 Jan; 2028 Apr; 2028 Jul; 2028 Oct; 2029 Jan; 2029 Apr; 2029 Jul
Art | Outsource | Character / Concept Art | Vendor | 10000 | [39 empty] | 0 | 0 | 0 | 0 | 3 | 0 | 7 | 10 | 100000 | bar: 2027 Aug to 2027 Oct; 2028 Jan; 2028 Apr; 2028 Jul; 2028 Oct; 2029 Jan; 2029 Apr; 2029 Jul
Art | Outsource | Marketing Art / Trailer | Vendor | 9000 | 2027 Aug: 0.5; 2027 Sep: 0.5; 2027 Oct: 0.5; 2027 Nov: 1; 2027 Dec: 1; 2028 Jan: 1; 2028 Apr: 1; 2028 Jul: 1; 2028 Oct: 1; 2029 Jan: 1; 2029 Apr: 1; 2029 Jul: 1 |  | 0 | 0 | 0 | 0 | 1.5 | 2 | 7 | 10.5 | 94500
Aud | Outsource | Voice Director | Vendor | 10000 | [39 empty] | 0 | 0 | 0 | 0 | 3 | 0 | 7 | 10 | 100000 | bar: 2027 Aug to 2027 Oct; 2028 Jan; 2028 Apr; 2028 Jul; 2028 Oct; 2029 Jan; 2029 Apr; 2029 Jul
Aud | Outsource | Voice Over | Vendor | 8000 | [39 empty] | 0 | 0 | 0 | 0 | 3 | 0 | 7 | 10 | 80000 | bar: 2027 Aug to 2027 Oct; 2028 Jan; 2028 Apr; 2028 Jul; 2028 Oct; 2029 Jan; 2029 Apr; 2029 Jul
[44 empty] | 3 | 27 | 141 | 84 | 115.5 | 76 | 505 | 951.5 | 9629500
Staffing Summary
[5 empty] | 2026 | [5 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
|  |  | Dept |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Total MM
|  |  | Art |  | 0.5 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4.5 | 4.5 | 4.5 | 6.5 | 6.5 | 6.5 | 6 | 6 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 3.5 | 5.5 | 3.5 | 156.5
|  |  | Code |  | 0.5 | 2 | 2 | 2 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 9.5 | 9.5 | 9.5 | 10 | 10 | 7.5 | 7.5 | 7.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 204.5
|  |  | Production |  | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 99
|  |  | Design |  | 1 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 7.5 | 7.5 | 7.5 | 8.5 | 8.5 | 8.5 | 9.5 | 9.5 | 8 | 8 | 8 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 250.5
|  |  | Level Art |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 38
|  |  | UI |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 39
|  |  | Aud |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 30
|  |  | QA |  | 0 | 1 | 1 | 1 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 134
|  |  | Total |  | 3 | 9 | 9 | 9 | 23.5 | 23.5 | 23.5 | 23.5 | 23.5 | 23.5 | 28 | 28 | 28 | 38.5 | 38.5 | 38.5 | 38 | 38 | 35.5 | 30.5 | 30.5 | 27.5 | 22.5 | 22.5 | 27.5 | 22.5 | 22.5 | 27.5 | 22.5 | 22.5 | 27 | 22 | 22 | 27 | 22 | 22 | 27 | 22 | 951.5
|  |  | Month |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Note on D6: Author: This row is a lookup for the phase of dev. Don't merge them, but do change them to match the row above